## Module1
Question | Type | Option A | Option B | Option C | Option D | Option E | Option F | Option G | Option H | Option I | Option J | Option K | Option L | Option M | Option N | Option O | Option P | Option Q | Option R | Correct Answer
Which of the following are true regarding the attributes of a standard Configuration Items List (CIL)? (Select all that apply.) | multi_select | In order to determine whether a configuration item is a draft or released, it is enough to examine the structure of its version number. | The name of the file of a configuration item must include the version number so when an item is distributed, it is absolutely clear what version is the latest. | The name of the file of a configuration item must include both the version of this item and the date, so when an item is distributed, it is absolutely clear when it was changed last. | The CI List itself has a version number, which is in addition to individual versions of each item. | [14 empty] | A,D
Consider the goal of the project is to develop a CMS (Content Management System). During the initial meeting of the project team, a decision is to be made regarding the name of the file that contains the common report. Such a report is supposed to assemble all deliverables. Each week a new deliverable is appended to the same document. So, at the end of the project, the comprehensive report includes all artifacts and is ready for the final presentation. Provide a recommendation to the team by selecting from the following five choices the one most fitting name for the report. | multiple_choice | REPORT NAME: Report Content Management System version 0.1. | REPORT NAME: Final report Content Management System. | REPORT NAME: Content Management System Requirements and Team Composition | REPORT NAME: Report Content Management System July 5 2018. | REPORT NAME : First week report Content Management System. | [13 empty] | B
Members of a team shall converge on a consistent way to version their deliverables. What versioning standard do we follow in this class, when naming each submission of the project report ? Select one from these three given options | multiple_choice | <class> <team #> <submission #> | <team #> <module #> <date> | <topic> <class> <semester> | [15 empty] | C
Consider the column of a CI List titled "Asset Name." From the list below select appropriate line items for this column. | multi_select | Brainstorming solutions to customer complaints | UML Diagram with use cases | Architectural spec | Preparation for a meeting with senior management | Throwing around ideas - to see which idea could stick | [13 empty] | B,C
Select from the following four choices all that apply. The reason a Configuration Items List could be useful is because... | multi_select | Forget about version numbers for a minute. What is most important is that the CI list documents everything you need to deliver. Without such a list, I am sure something is bound to be missed. | CI List maps one-to-one into Estimation Record. | It gives you the key information about which versions are the latest. | With each distribution of the list, you are able to recognize if an important item was added or deleted. | It documents your decision and identifies which items are controlled and which items are not controlled. | [13 empty] | A,C,D,E
Which of the following are prudent actions, as per SCM best practices discussed in the class? | multiple_choice | Keep important documents on individual desktops. | Promote within the organization or release major changes before a peer review or an approval. | Distribute documents as attachments instead of distributing them via a link. | Maintain duplicate documents in a library. | Assign to documents only those names that definitely reflect the documents content and the librarys convention. | [13 empty] | E
Which of the following statements use the taxonomy of code control correctly? | multi_select | A "conflict" is likely to occur when multiple changes to the same piece of code are integrated. | A common case of "rebasing" is to regularly synchronize deployed into projects' branches. | In order to release a project, it is necessary to "promote" it into deployed. | A common case of "rebasing" is to advance code changes from a project's branch into deployed. | In order to release a project, it is necessary to "rebase" it into deployed. | A "conflict" is unlikely to occur when two code changes are incorporated into two unrelated pieces of code. | [12 empty] | A,B,C,F
From the course notes, the scope of SCM (Software Configuration Management) covers the following (select the option with the best fit): | multiple_choice | code, internal docs and tools | code, tools, internal docs, user docs | only code | code and internal docs | [14 empty] | B
Of the three transitions between versions, which transition is the most clear, understandable, and prudent? | multiple_choice | from 1.3 to 2.9 | from 7.8 to 5.2 | from 2.5 to 2.6 | [15 empty] | C
Any CM repository bumps the version of an asset in response to even a minuscule change. Why is automatic versioning insufficient? Why do we need to manually change the version of, for example, a functional spec? (Select the reason that is most appropriate.) | multiple_choice | Because automatic versioning cannot be trusted, as it could miss a software change. | Because a versioning standard represents a certain agreement and a common understanding. One is able to see how many major customer releases were shipped or whether the current version is a draft. | [16 empty] | B
A message that a developer manually adds to a commit should cover the following information. (Select all that apply). In this quiz, we assume that defects, stories and code are maintained in three independent systems that have no automatic connection. | multi_select | Why the change was made | When this change was done | Which stories (requirements) this change relates to | What defects this change addresses | Who accomplished the change | What was changed, including names of specific files | [12 empty] | A,C,D
Regarding the baseline audit discussed in the class, which one of these two statements is true? | multiple_choice | A baseline audit checks the integrity between baselines. Artifacts have to be traceable to each other between different baselines, although they might NOT be traceable within each baseline. | A baseline audit checks the integrity of each baseline. Artifacts have to be traceable to each other within each baseline, although they might NOT be traceable between different baselines. | [16 empty] | B
A software engineer should utilize a prudent branching and merging strategy. Consider the three statements below and select those statements that are reasonable conclusions. | multi_select | If two software engineers do not have any conflicts while merging their two objects into seemingly unrelated parts of the codebase, then ten engineers trying to merge their twenty fixes into the same file will surely not have any conflicts that they will need to manually resolve. | If two software engineers have a conflict while merging their two objects into a seemingly unrelated part of the codebase, then ten engineers trying to merge their twenty fixes into the same file will have a strong chance of a conflict that they will need to manually resolve. | If ten engineers merging their twenty fixes into the same file do not have any conflicts, then two software engineers are unlikely to have conflicts while merging their two objects into seemingly unrelated parts of the codebase. | [15 empty] | B,C
In the beginning of a project, it is important to select items that need to be controlled. Consider three levels of SCM control. Which of the following statements are true? | multi_select | A piece of code that is being developed on a private branch and has not been offered for a peer review yet...belongs to Version Control. | A Functional Spec that has been signed off on by Engineering and Product Management...belongs to Change Control. | A yellow sticky with a reminder that your manager leaves at your desk...belongs to Version Control. | Comments resulting from a code review...belong to Version Control. | Defects that originated as a result of a system test...belong to Change Control. | [13 empty] | A,B
The book of Mario Moreira Adapting Configuration Management for Agile Teams emphasizes the difference between adopting versus adapting the infrastructure. The paper by Richard Bach The Highs and Lows of Change Control stresses the importance of deliberately selected levels of control during software development. Select those statements that are true. | multi_select | A small team supporting the Celebrity News website needs less controls than DoD (Department Of Defense) contractor supplying equipment to TSA (Transportation Security Administration). | Mature teams do not follow any standard Configuration Management practices. | A thousand people organization, distributed over a dozen countries needs more controls than a ten-people collocated team. | A team of fifty engineers designing a complete solution (hardware, software, manufacturing) for a highly-regulated medical devices industry needs more controls than a similar-size organization operating in an non-regulated space. | [14 empty] | A,C,D
Suppose you are adopting a defect prevention process in your organization. As a first step, you want to distinguish common defects and then to assure such common defects are addressed ahead of all other defects. Consider the following checklist that separates "common defects" from other defects let's call them "flukes." (Select from the following statements all that are true.) . | multi_select | If ten different types of intermittent failures have the same root cause, then such a root cause corresponds to a "common" defect. | A defect that causes repeated failure on the same customer site, every ten hours is a common defect. | If ten software engineers, while working independently from each other, inserted the same defect in different parts of the code base, such a defect is surely a "fluke." | A defect that manifests itself on ten customer sites is a common defect. | [14 empty] | A,B,D
Consider the following scenario. The first month of the "Test&Fix" phase brought an unusually large number of defects. So management allocated a third of all software engineers to bug fixing. During the next month, the number of newly discovered defects grew even larger, which forced management to allocate two-thirds of all engineers to resolving these issues. Customers had to be informed that the release delivery was delayed. The next month resulted in an even greater number of newly recorded defects. Management halted new development, announced an "all hands on deck" policy and allocated all engineers to resolving these problems. At this moment of contention, a meeting was held to zero in on the root cause of this high discovery rate. From the list below select the one root cause that is least appropriate. . | multiple_choice | The Tester suggested that fixing defects should focus on the root cause of each issue instead of correcting the manifestations of a deep down fault. | The Architect explained the great number of defects by citing minor inconsistencies in the user interface implementation. | Everyone suspected that testers were sabotaging the process by delaying the recording of defects. If testers were announcing defects as soon as they were discovered, then bug fixing could go faster. | The Marketing Manager implied that the problem was with the overall company strategy. She requested that they ship software immediately, so as to let customers find defectsâ€”since customers are unable to find as many issues as professional testers could find. | The UX Engineer stated that this was a fundamental problem with architecture and the original system design had to be re-drafted. | [13 empty] | D
Analyze the following scenario. Six members of a scrum team estimate their backlog using the planning poker method. One person, who is particularly experienced with a certain story, shows the card with 8 points. The other five members, who do not have much experience with this type of story, show the card with 3 points. Which estimate is most likely accurate? | multiple_choice | 8 points | 3 points | average among all members participating in this estimate ... ((3 * 5) + 8) / 6 = 4 points | [15 empty] | A
Which of the following are true regarding an estimation procedure using the planning poker method? | multi_select | No card with the number 12 exists, since the number 12 is not a part of the Fibonacci sequence. | If someone shows an "infinity" card, it means that the estimate is infinitely small. | If someone shows an "infinity" card, it means that an estimate does not fit into the iteration capacity, suggesting that the corresponding story should be split. | [15 empty] | A,C
The rationale for selecting an estimation technique should be clear. Some methods are simple and other methods are complex. Some methods apply to the beginning of a project and others apply to its end. Various methods yield results with very different accuracy. Considering two very common estimation methods, Analogy and Decomposition, select the order in which these methods should be used. At what time is each of the two options more appropriate? | multiple_choice | The Decomposition method should be used first, in the beginning of a project; then the Analogy method should be used. | The Analogy method should be used first, in the beginning of a project; then the Decomposition method should be used. | [16 empty] | B
Which of the following are true regarding development estimates? (Select all that apply.) | multi_select | The number of story points is a direct measure of customer value. | Longer programs have a smaller margin of error. | The logical order of initial project activities is to start with estimating then proceed into scheduling and finish with commitment. | Estimation is an inherently iterative process. | Estimates should never be provided by the people who will do the work. | Estimates are usually overoptimistic. | The precision with which estimates are communicated should be at least two orders of magnitude greater than the possible accuracy of these estimates. | The logical order of initial project activities is to start with commitment then proceed into scheduling and finish with estimating. | [10 empty] | C,D,F
Suppose your project is halfway through completion. You have submitted four project-level estimates already. A senior manager is challenging your second estimate number and is asking you to redo it. What is the prudent response to this request and what activity will yield a more useful result? | multiple_choice | You should go back and redo the second estimate, using the same technique (and data) as you used previously. | You should keep moving forward and use the estimation technique (and data) that is congruent with your current position in the project life cycle. | [16 empty] | B
A software engineer came to HR department with a question. His manager asked to document an estimate - when the module will be done. Engineer is afraid of repercussions, since there are many reasons why the work can be delayed and the original estimate can become inaccurate. Question is whether to tell the truth? Please select the most fitting option, how HR should respond to this question? | multiple_choice | Response . Invite your manager for a cup of coffee; talk about your children and hobbies, and by all means avoid talking about this estimate, in a hope that the manager will forget about the topic all together | Response . Calculate the estimate to the best of your abilities and communicate it to the manage | Response . Add a large buffer to your estimate, for example, multiply it by the factor of three. Communicate to manager the exaggerated number without mentioning how it was arrived at. | [15 empty] | B
Suppose a senior manager provides a well-thought-through motivation and direction to the project team. Which of the following statements fit better into a prudent estimation practice? (Select all that apply.) | multi_select | We need to renegotiate our estimates. | We need to discuss and resolve our assumptions before the next estimation cycle. | We need to renegotiate our commitments. | [15 empty] | B,C
Rank the following activities in order of their potential impact on improving estimation accuracy on your project and select the answers below that reflect your rankings. (Select all that apply.) a) Hire an experienced organizational estimator, a Nobel Prize winner, who is well-known for his aloof and mathematical approach to estimation b) Allocate additional time to calibrate, verify and re-calibrate estimation measurements c) Stabilize project requirements and make sure any additions, deletions and changes to requirements are accounted for d) Assure defects are fixed close to the point of their origin and do not cause surprises at the end of a life cycle. | multi_select | (c) and (d) should be ranked higher than (a) and (b) | (a) and (b) should be ranked lower than (c) and (d) | [16 empty] | A,B
Consider the estimation record for a project with three columns (a) Size (b) Effort and (c ) Duration. What is your interpretation of the TOTAL for the column (a) Size? | multiple_choice | Response 2. Calculate the estimate to the best of your abilities and communicate it to the manager. | Response 3. Add a large buffer to your estimate, for example, multiply it by the factor of three. Communicate to manager the exaggerated number without mentioning how it was derived. | Response 4. Speak with the manager about project expectations. Then tell him exactly what he wants to hear. Remember that if you tell him the truth, it might destroy your career, it might destroy the career of your manager and it might destroy the whole company including my career inside HR . | Response 1. Invite your manager for a cup of coffee; talk about your children and hobbies, and by all means avoid talking about this estimate, in a hope that the manager will forget about the topic all together. | [14 empty] | A
With reference to the topic discussed in class titled, "DNA of a Story Point," suppose you have three teams, with the first two as follows: Team #1 (consisting of UX engineers) defines a story point as drafting five mock-up screens, conducting a peer review to converge on these screens and incorporating changes. Team # 2 (which is involved in writing code) defines a story point as participating in two code reviews and developing and testing 25 lines of code on a private branch. (Select all the following statements that are true.) | multi_select | Suppose Team #1 has to develop one hundred screens. Without looking into details, this activity will account for approximately five story points. | Suppose Team #1 has to develop fifty screens. Without looking into details, this activity will account for approximately ten story points. | Team #3 has to establish its own definitions and references. | Team #3 (involved in developing and executing test cases) could simply reuse the same definitions of a story point that Team #2 has documented already. | [14 empty] | B,C
An organization maintains several product development life cycles to be used by various projects. At the beginning of any project there is a decision to be made as to which life cycle to use. A team decided to follow an alternative product development life cycle. Instead of defining personas and documenting requirements, this team decided to start with building a prototype. Then, if the prototype was approved, the team would return to the very beginning and follow the prudent process, including the verification steps of peer reviews, and testing. In fact, that is exactly what has happened, as the prototype was successful and was blessed by senior management. Now the team needs to make the decision...what to do with the prototype? Here are two options. | multiple_choice | Mary intimated her nostalgic feelings toward the prototype and said that the team should preserve the prototype while extending it to a comprehensive system. | John suggested that they completely abandon the prototype and start developing a new system from scratch, since one is unable to enter the same river twice. | [16 empty] | B
Suppose you belong to a high-maturity team. There is a checklist in front of you offered by Steve McConnell (from his book Software Estimation) focusing on your estimation practices. Of the thirteen questions listed below, twelve questions are useful and appropriate and one question is inappropriate. Please mark the twelve that are useful and appropriate. | multi_select | Are your initial estimates part of a series of estimates that will become more accurate as the project moves into the narrow part of the cone of uncertainty? | Is the productivity assumption underlying your estimates comparable to productivity actually experienced on past projects of similar sizes? | Are your estimates created using multiple techniques that converge to similar results? | Are the people who are going to do the work involved in creating the estimates? | Do your estimates include a non-zero allowance for the impact that project risks and inherent uncertainty will have on effort and schedule? | Are your estimates expressed with precision that match their accuracy (e.g., are the estimates expressed as ranges or coarse numbers if it's early in the project)? | Was the schedule estimate computed based on underlying estimates of effort and size, rather than being directly estimated ? | Are all elements of your project included in your estimates, including installation program, data conversion, cutover from old system to new system, etc.? | If your estimate was negotiated, were only the inputs to the estimate negotiated, not the outputs and not the estimation process itself? | Do you use a standardized procedure to create your estimates? | Is your estimation process free from pressure that would bias the results? | Do you have your estimates reviewed by an expert estimator? | Is your management using overoptimistic estimates as part of the motivation strategy to encourage engineers to go the extra mile? | [5 empty] | A,B,C,D,E,F,G,H,I,J,K,L